FAYETTEVILLE TECHNICAL COMMUNITY COLLEGE HIGH-QUALITY COURSE DESIGN PROGRAM • INSTRUCTIONAL SUPPORT & QUALITY ASSURANCE

How Long Does Quality Course Design Actually Take?

A Data-Informed Estimate for Administration & Resource Planning

Angela Westmoreland, M.Ed.  |  FTCC HQCDP  |  Spring 2026

Why This Document Exists Quality online course design is invisible when it is done well — administrators see a finished Canvas shell, not the weeks of work behind it. This document provides concrete, evidence-based time estimates for every stage of building a QM-aligned, RSI-compliant, HQCDP-certified course. It is intended to inform decisions about faculty release time, course development contracts, and instructional design staffing.

Part I: The Honest Numbers

The following estimates are based on actual time tracked during the development of HIS-131 and HIS-132 as HQCDP exemplar courses. They reflect the work of an experienced instructional designer with 20+ years of experience and four QM certifications — not a faculty member building their first online course.

Important Caveat These are expert-level estimates. A faculty member building their first QM-aligned course without dedicated instructional design support should expect 1.5–2× these figures. A faculty member building with full instructional design partnership may come in at or below these numbers.

Phase-by-Phase Time Breakdown

| Phase / Task | Est. Hours | What This Involves |
| --- | --- | --- |
| Course architecture & CLO mapping | 8–12 hrs | Mapping NCCCS outcomes to CLOs, verifying Bloom's levels, designing the 8-module inquiry framework, establishing the milestone pattern |
| Module-level MLO development (×8) | 12–16 hrs | Writing 3 MLOs per module, crosswalking each to CLOs, verifying Bloom's alignment at module level |
| Instructional content planning (IC 1–3) | 8–10 hrs | Selecting OER chapters, identifying key concepts per chunk, writing IC descriptions for course map |
| Primary source research & curation (IC 4, ×8) | 10–14 hrs | Researching, evaluating, and selecting 8 primary sources; verifying free access, word count, pedagogical fit, and URL stability |
| Learning activity design (LA1–LA4, ×8) | 16–20 hrs | Designing all LA types per module, writing item stems, building Canvas New Quizzes structures, verifying auto-gradability |
| Assessment design & rubric writing | 10–14 hrs | Writing DB prompts, portfolio piece instructions, quiz questions, midterm/final, and all associated rubrics |
| Course map production | 8–10 hrs | Completing the official FTCC course map template with all alignment documentation, workload calculations, and QM verification |
| Teaching plan production | 6–8 hrs | Writing full student-facing teaching plan with module guides, design justifications, and IC 4 documentation |
| Workload calculation & compliance documentation | 4–6 hrs | Calculating student hours using CITL methodology, verifying 135-hr compliance, documenting RSI touchpoints |
| Canvas shell build & QM review | 12–18 hrs | Building all module pages, uploading activities, configuring gradebook, conducting QM self-review, revising |
| Quality review & revision cycles | 8–12 hrs | Peer review, revision, alignment check, accessibility review, final certification submission |
| TOTAL — Expert Designer | 102–140 hrs | Approximately 13–18 working days of dedicated course design time |

Part II: What This Means in Practice

For a faculty member without instructional design support:

- Estimated range: 150–220 hours for a first QM-aligned course build

- This is 4–6 weeks of full-time work — on top of teaching, service, and other obligations

- Without release time or compensation, this work happens at nights and weekends, producing lower quality and higher faculty burnout

- This is the primary reason course quality is inconsistent across the institution

For a faculty member with HQCDP partnership support:

- Faculty time: 40–60 hours (subject expertise, content decisions, review, approval)

- Instructional designer time: 60–80 hours (architecture, documentation, Canvas build, QM verification)

- Total team time: 100–140 hours — but distributed correctly between the people best positioned for each task

- Result: Higher quality, faster timeline, and a faculty member who understands their course design rather than being overwhelmed by it

The ROI Calculation One instructional designer supporting 6 faculty per semester can produce 6 QM-certified, RSI-compliant courses that would otherwise each take 150–220 uncompensated faculty hours. Total faculty time saved: 900–1,320 hours per semester. At an average faculty hourly rate of $35–$50, that is $31,500–$66,000 in faculty time — per semester — redirected from course production to teaching, student support, and scholarship.

Part III: The Hidden Cost of 'Good Enough'

When courses are built without this investment, the institutional costs are real but distributed invisibly:

- Student outcomes: Misaligned activities produce students who complete work without demonstrating learning — increasing DFW rates and reducing retention

- Federal compliance risk: Courses without documented RSI expose the institution to Title IV audit risk — fines and repayment obligations for non-compliant distance education

- Accreditation exposure: SACSCOC requires evidence of student learning outcomes assessment — courses without CLO alignment documentation create audit vulnerabilities

- Faculty morale: Faculty who build poor courses often know they are poor and feel unsupported — a contributing factor in turnover and disengagement

- Reputational cost: Student course evaluations and word-of-mouth enrollment decisions are directly affected by course quality

Part IV: What FTCC Has Invested — and What It Has Produced

The HQCDP exemplar courses (HIS-131 and HIS-132) represent approximately 240 hours of combined instructional design and faculty time across both courses. In return:

- Two fully QM-certified courses (22/22 Essential Standards each) ready for formal peer review

- A replicable model that reduces subsequent course builds by 30–40% once the framework is established

- A complete template library (course map, teaching plan, workload calculator) that any discipline can adapt

- Documented federal compliance — RSI at 10× minimum, student hours at 102% of target

- A GitHub-hosted interactive dashboard that makes the model transparent and scalable

- A professional development framework that faculty can use to build their own courses with support

The Bottom Line for Administration Quality course design is not a luxury — it is a compliance requirement, a retention driver, and a faculty support system. The question is not whether to invest in it, but whether to invest proactively through structured support or reactively through course corrections, audit responses, and faculty turnover.